# HealthConnect Clinic — Week 5 Project Summary

Data Analytics Track | AnalystLab Africa Experience Lab

# 1. Planned for Week 5

Move from Week 4's planning (business questions, candidate KPIs, data quality review) into full exploratory analysis: calculate the five proposed KPIs, run statistical tests to confirm which patterns are meaningful, build a dashboard, and generate business insights and recommendations.

# 2. What Was Actually Completed

- Re-confirmed data quality (no duplicates, no logical inconsistencies, minor explainable missingness).

- Calculated all five KPIs proposed in Week 4, each with a chi-square significance test.

- Ran deeper exploratory cuts across appointment characteristics, patient characteristics, history, reminders, waiting time, distance and cancellations.

- Identified a compounding effect between booking lead time and prior no-show history.

- Built a six-panel analytical dashboard summarising all key findings.

- Produced 7 business insights and 5 concrete recommendations.

- Saved a processed dataset (with derived risk/segment columns) separately from the original source file.

# 3. Key Findings / Development Outcomes

- 48.5% overall no-show rate; 53.7% of all slots go unused as booked once cancellations are included.

- Booking lead time is the strongest driver (27.8% → 60.5% no-show rate, p<0.001).

- Prior no-show history is the second-strongest driver (43.5% → 68.8%, p<0.001), and compounds with lead time to reach 80-81% in the highest-risk segment.

- Reminders are statistically significant but modest overall, and matter far more for higher-risk patients (~10-point reduction) than lower-risk patients (~3-point reduction).

- Distance is a threshold effect: flat below 20km, rising sharply beyond it.

# 4. Major Challenges Encountered

- The Sunday-appointment inconsistency identified in Week 4 remains unresolved, with no stakeholder clarification available yet — it was carried forward as a documented, unaddressed data quality flag rather than corrected.

- Distinguishing statistical significance from practical importance required care — several effects (e.g. distance, reminders) are statistically real but modest in absolute size, which shaped how the recommendations were framed.

# 5. Important Decisions Made and Why

- Kept all five Week 4 KPIs rather than narrowing to three, since all five were grounded in statistically significant patterns worth reporting.

- Chose to segment the reminder-effectiveness KPI by patient risk tier rather than reporting only the overall effect, since the overall figure understated how much reminders matter for higher-risk patients.

- Left the Sunday-appointment records unmodified rather than dropping or correcting them, in line with the instruction not to alter source data without stakeholder guidance.

# 6. Changes to the Week 4 Approach

No changes to the overall approach were needed — Week 5 executed the plan proposed in Week 4 in full. The one refinement was to the reminder-effectiveness KPI, which was extended to include a risk-tier breakdown once the overall effect turned out to be smaller than expected.

# 7. Cross-Track Collaboration Completed

Shared the five KPI definitions and statistically significant risk segments (lead time, prior no-show count, and their compounding effect) with the Data Science track, to help prioritise candidate features for their Week 5 baseline no-show prediction model.

# 8. Remaining Work

- Resolve the Sunday-appointment data quality flag with AnalystLab/clinic stakeholders.

- Explore whether an agreed imputation approach is needed for the small amount of missing distance and waiting-time data.

- Extend the dashboard into a more interactive format if a BI tool (e.g. Power BI/Tableau) is adopted in later weeks.

# 9. Proposed Focus for Week 6

- Track the same KPIs over time if additional data becomes available, to see whether patterns are stable.

- Support the Data Science track in evaluating their baseline model results against the segments identified here.

- Investigate the cancellation population (5.3%) specifically, to assess how many of those slots could realistically have been rebooked.